## Ark1
WEBSITE PROJECT: LOFTHUS FRUKT AND SAFT |  |  |  | NOVEMBER | [5 empty] | DECEMBER
Start Date: 25/11-19 ¦ End Date: 13/11-19 | RESOURCES | STATUS | DAYS | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
PLANNING |  |  | 2 D
On-site meeting - Customer research | Front-end/Copywriter | NOT STARTED | 1 D
Tour (production process) | Front-end/Copywriter | NOT STARTED | 1 D
Research other similar websites | Front-end | NOT STARTED | 1 D
WEBSITE BUILD |  |  | 16 D
Sketching layout | Front-end | NOT STARTED | 1 D
Build layout HTML | Front-end | NOT STARTED | 11 D
About us | Front-end | NOT STARTED | 1 D
Contact us | Front-end | NOT STARTED | 1 D
Production site | Front-end | NOT STARTED | 1 D
Order page | Front-end | NOT STARTED | 1 D
Checkout page | Front-end | NOT STARTED | 2 D
Add CSS | Front-end | NOT STARTED | 5 D
Adding images | Front-end | NOT STARTED | 1 D
Adding articles, text, fonts | Front-end | NOT STARTED | 2 D
Cleaning code | Front-end | NOT STARTED | 1 D
Finalize website / design | Front-end | NOT STARTED | 2 D
DESIGN / FINAL PHASE DEVELOP |  |  | 5 D
Sketching identety elements | Designer / Front-end | NOT STARTED | 4 D
Customer feedback / Presentation | Front-end | NOT STARTED | 1 D
PROMOTE / MARKETING |  |  | 16 D
Research | Copywriter | NOT STARTED | 5 D
User experience | Copywriter | NOT STARTED | 1 D
Landing page | Copywriter | NOT STARTED | 2 D
Copywriting, about us, production | Copywriter | NOT STARTED | 5 D
Promotion | Copywriter | NOT STARTED | 4 D
Finalize promote / marketing | Copywriter | NOT STARTED | 1 D
PHOTOGRAPHY |  |  | 3 D
Location shoot (production) | Photographer | NOT STARTED | 1 D
Area shoot (process and hardanger) | Photographer | NOT STARTED | 1 D
Source images | Photographer/Front-end | NOT STARTED | 1 D
FINALIZE PRODUCT |  |  | 1 D
Launch website | Front-end |  | 1 D